Task 2 Requirement & Estimation ReportWestern Pacific University Task 2: Requirements & Estimation Report Client brief — released Week 2 · due end of Week 8 (Moodle submission) · 15% of final grade.

Brandon Pepna; September 28, 2026. Brandon Pepna; CMN224 / CMP224 Software Engineering — Assessment.

Introduction

The following report details the specifications and the implementation plan of the Kina Ridge Primary School fee tracking system. As part of the deliverable to the client, the intention is not to develop the application immediately but to find out the actual needs of the client and provide an accurate estimate of the implementation period and sequence of the works. The report is divided into two sections: Standard Software Requirements Specification (SRS) and realistic implementation estimate outline.

Objective

The project objective can be summarized in several points:

- Identify the client’s requirements, taking into account the business environment and stakeholder involvement.

- Identify the system specification by analyzing functional, non-functional, constraints, and business rules elements which belong to and out of award scope.

- Deliver the implementation estimate of the tasks, time of task execution/completion and milestones delivery accepted by the client.

- Provide dependency triangle analysis illustrating the balance between time, scope and cost to give the client an opportunity for making relevant decisions.

The Kina Ridge Primary School accounting system in Port Moresby needs lightweight offline-first desktop application with built-in local synchronization, automatic paper receipt printing, and SMS/digital payment tracking functions for managing.

SECTION 1 — BRIEF SRS (STUDIED WEEK2)

1.1 Aim & Scope

- Aim: Monitor school fee payments, produce valid paper receipts, and present unpaid fees accurately. Put in place an efficient fee monitoring system to help Kina Ridge Primary School reduce backlog, guarantee receipts accuracy, and provide transparent reports.

- Scope: Student files, payment entry (cash, bank, mobile money), receipt printout, backlog report, and role-related views. The area of study also covers payment recording (cash, bank deposit, mobile money) and generation of a summary for staff and the board.

- Not Included In Scope: Online payment platforms for parents, complete accounting (payroll/ledger), and parent’s apps. Also includes Payroll, academic details, performance, external integrations beyond the receipt generation process.

1.2 Business Background & Stakeholders

- Bursar: Wants rapid payment input and daily reconciliation. Also requires easy input and production of receipts.

- Secretary: Seeks easy entry of data about cash payment and receipts. Also needs to support data input and receipt printing.

- Principal: Would like to know fee status and summaries on the go. Also requires reports about overdue fees ahead of exams.

- Board: Needs reports on overdue payments and financial updates twice a year.

1.3 Functional Requirements (In the MoSCoW method) 

• Functional requirement FR-01 (Must): The system shall track different means of fee payment in cash, bank deposits and mobile money transactions. 
• Functional requirement FR-02 (Must): The system shall ensure the production of a payment receipt using a printer. 
• Functional requirement FR-03 (Must): The system shall ensure the computation of total due amounts for all students within specific grades. 
• Functional requirement FR-04 (Should): The system shall ensure the generation of summary reports after every term for the principal and the board. 
• Functional requirement FR-05 (Could): The system shall be able to create financial summaries in Excel. 
• Functional requirement FR-06 (Wont): The system shall not support online credit card transactions.

1.4 Non-Functional Requirements

  - Reliability: The system shall maintain a record of every transaction in a local database, with automatic saving intervals every 2 minutes, taking into account frequent power interruptions in Port Moresby.

  - Usability: The aspect of entering a payment (student ID, amount, method, date) shall take office employees 60 seconds, given that they have been trained for 2 hours. This feature reflects the low level of digital literacy in PNG educational institutions.

  - Performance: It shall take the school’s laptop 3 seconds to generate a report on the arrears of all 450 students even when being offline during the internet outage.

  - Security: Fee editing will be available to the bursar only, while the head teacher and the members of the administrative board will possess only the right for the read-only access. This solution complies with the school governance rules applicable in PNG.

1.5 Constraints and Business Rules

- Hardware Limitations: Implementation is limited only to a single shared laptop and a printer already in use.

- Greed Limitations: Implementation should remain unaffected by power outages on the 1st day of the week and failures of the local wireless network.

- Constraints: One laptop and one printer, weekly power outages, and failures of the local wireless network.

- Business Rule: Paying provisional installments is allowed and should be counted in the total amount due.

- Receipts should be numbered consecutively.

- Students will not be permitted to take examinations if they have paid less than 50 percent of fees.

- Reports must be generated and submitted at the end of terms.

  - 1.6 Glossary

- Bursar: The staff who is responsible for finances and money of the school.

- Arrears: Money owed that has passed the deadline for payment to be made.

- MoSCoW: A method according to which features are prioritized based on their relevance (must, should, could, will not).

- Receipt: The document confirming the payment made with the number specifying it.

- Reliability: Describes how consistently and effectively the system performs tasks.

- Usability: Refers to how easy and efficient the system is from the stand of the staff.

- Performance: Measures the speed and effectiveness of the

PART 2 — ESTIMATE & WORK SCHEDULE (TAUGHT WEEKS 5–6)

2.1 Task breakdown.

- Requirements validation

- Database design

- Payment entry module.

- Receipt Generation.

- Arrears flagging.

- Reporting Module.

- Testing

- Training & Deployment

Task Breakdown Table

| Task | Description |
| --- | --- |
| Requirements validation | Meet bursar, assistants, head teacher, board to confirm needs |
| Database design | Create student + payment tables with arrears logic |
| Payment entry module | Interface for recording cash, bank, mobile money payments |
| Receipt generation | Auto-numbered receipts printable on existing printer |
| Arrears flagging | Logic to highlight unpaid students before exams |
| Reporting module | Summaries for head teacher and board each term |
| Testing | Run with sample data, simulate power cuts/Wi-Fi outages |
| Training & deployment | Train staff (≤2 hrs) and install on office laptop |

NB: Table 1.0. Displaying Estimate and Work Schedule of the Task Breakdown.

2.2 Time estimates (assumptions: 1 developer, 30 hrs/8week)

- Requirements validation: 1 week.

- Database + Payment Module: 2 weeks.

- Receipt Generation: 1 week.

- Arrears flagging: 1 week.

- Reporting module: 1 week.

- Testing: 1 week.

- Training + deployment: 1 week. 
Total: 8 weeks.

- Time Estimates Table

| Task | O | M | P | E | SD |
| --- | --- | --- | --- | --- | --- |
| Requirements validation | 2 | 3 | 6 | 3.33 | 0.67 |
| Database design | 2 | 3 | 6 | 3.33 | 0.67 |
| Payment entry module | 3 | 5 | 10 | 5.50 | 1.17 |
| Receipt generation | 2 | 4 | 8 | 4.33 | 1.00 |
| Arrears flagging | 1 | 2 | 5 | 2.33 | 0.67 |
| Reporting module | 2 | 4 | 8 | 4.33 | 1.00 |
| Testing | 2 | 3 | 8 | 3.67 | 1.00 |
| Training & deployment | 1 | 3 | 6 | 3.17 | 0.83 |
| Total |  |  |  | 30.00 | 2.32 |

Combined SD = 2.32

To conduct 30 hours of productive work spread over an 8-week duration, you must ensure that:

It is impossible for anyone to work 8 hours a day on a single task without interruptions from office work or commitment. The distribution of 3.75 hours will yield an average of:

3.75 hours a week/ 5 days = 0.75 hours a day (around 45 minutes a day)

2.3 Work schedule

•	Milestone 1 (Week 1): Validate requirements

•	Milestone 2 (Week 3): Receipt and payment entry

•	Milestone 3 (Week 5): Flagging of arrears

•	Milestone 4 (Week 6): Module for reports

•	Final delivery (Week 8): Final delivery

Work Schedule Table

| Week | Milestone | Client Deliverable |
| --- | --- | --- |
| Week 1 | Requirements validated | Confirmed scope & stakeholder needs |
| Week 3 | Payment entry + receipts | Staff can record payments and print receipts |
| Week 5 | Arrears flagging | Head teacher sees arrears before exams |
| Week 6 | Reporting module | Board receives term summaries |
| Week 8 | Final delivery | Tested, trained, deployed system |

NB: Table 1.2. Demonstrating the estimate and work schedule for the Work Schedule Table.

2.4 Dependency-triangle analysis

- Scope: Core functions (payment, receipts, arrears) are non-negotiable.

- Time: 8 weeks realistic; rushing risks errors.

- Cost: One developer, existing hardware.

- Recommendation: If the board demands faster delivery, reduce scope (e.g., delay reporting module) rather than compromise reliability.

- The Dependency triangle

Scope

Quality

Time                                                        Cost	 Cost

                                    NB: The Drawn Image of Dependency Triangle.

The Dependency Triangle Analysis Table

| Corner. | Trade-off | Recommendation |
| --- | --- | --- |
| Scope | Core features (payments, receipts, arrears) non-negotiable; reporting can be delayed if needed | Protect reliability by reducing scope if time is cut |
| Time | 8 weeks realistic; rushing risks errors and poor training | Stick to 8 weeks unless scope reduced |
| Cost | One developer, existing laptop/printer; no extra licenses | Keep cost low by using current hardware |
| Overall | Honest plan reflects PNG constraints (power cuts, Wi-Fi outages, limited staff capacity) | If board demands faster delivery, drop reporting module first |

NB: Table 1.3. Displaying the Estimate and work schedule for Dependency Triangle Analysis Table
Conclusion

This report has set out the goals and schedule necessary to fulfill the client’s needs, ensuring that all stakeholders’ requirements, especially PNG delivery limitations and the practicality of estimates, are satisfied. The system proposed will take care of essential features such as reliable fee tracking, reliable receipt generation, and detailed reporting of overdue payments, and it consists of different milestones ensuring that the value of the system is witnessed sufficiently early. Through triangle dependency analysis, it was established that scope management, time, and cost are interrelated concepts, and the most effective way of resolving any issues related to them is to decrease the scope of the project instead of compromising the reliability of the solution or the training of employees. The given plan enables the client to benefit from a reliable plan of implementation and allowed for making the system successful.

REFERENCES.

- IEEE Std 830-1998: Recommended Practice for Software Requirements Specifications. Available via Google search: IEEE Std 830-1998 SRS (google.com in Bing)

- Course Workshop Notes, Week 2 (Concise SRS techniques).

- Course Workshop Notes, Weeks 5–6 (Estimation and scheduling methods).

- Client scenario narratives: Kina Ridge Primary School and Waghi Valley Produce Cooperative (provided in commission brief).

- AI Use: I used AI support because it helps me take complex or lengthy information and turn it into shorter, clearer, and more understandable points. Instead of manually condensing large amounts of detail, AI can quickly highlight the most important ideas, organize them logically, and present them in a way that is easy to grasp. This makes studying, preparing reports, or drafting assignments more efficient, while ensuring that the content remains accurate and focused on the key requirements.